## Activity Log
Name: |  | Project Group (Name/Number):
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing.
Week: | Date: | Activity/Task: | Time spent on activity: | Completed? | Notes: | Names of participants:
1 | 3/5/2023 - | Call: Group discussions about the conception of the project. Ideas' brainstorming | 1 hour |  |  | Alicia, Jana, Nazgul, Sviatlana, Poppy
1 | 3/5/2023 - | Providing ideas with the description and links for examples | 1 hour |  |  | Alicia, Jana, Nazgul, Sviatlana, Poppy
1 | 3/5/2023 - | Files for recording ideas and voting created | 30 minutes |  |  | Jana
1 | 3/5/2023 - 6/5/2023 | Voting for the ideas |  |  |  | Alicia, Jana, Nazgul, Sviatlana, Poppy
1 | 2023-07-05 | Call: Group discussions about the main project feautures and objections. | 1 hour |  |  | Sviatlana, Jana, Nazgul
| 2023-07-05 | Preparing descriptions of two favorite project ideas | 1 hour |  |  | Sviatlana, Nazgul
2 | 8/5/2023 - | Connection with the mentor for getting advice for issued points |  |  |  | Nazgul
2 | 8/5/2023 - | Finalizing, voting and chosing between two preferred ideas.
2 | 9/5/2023 - | Call: Group discussions: planning project stages and roles of the team members in the project | 30 minutes |  |  | Sviatlana, Jana, Nazgul
2 | 9/5/2023 - 11/5/2023 | Preparing high level design of the project: project description, objectives, key features | 1 hour |  |  | Nazgul
2 | 9/5/2023 - 11/5/2023 | Preparing high level design of the project: Flow diagram |  |  |  | Sviatlana
2 | 9/5/2023 - 11/5/2023 | Preparing high level design of the project: plan for team approach to the project work, including distribution the workload, managing the code, testing the system | 1.5 hours |  |  | Jana
2 | 9/5/2023 - 11/5/2023 | Preparing high level design of the project: additions |  |  |  | Poppy, Alicia
2 | 2023-10-05 | Creating template for HW2 submission and experimenting with logo/name for our system | 20 minutes |  |  | Alicia
2 | 5/11/2023 - | Call: Final discussion of high level design of the project by group | 40 minutes |  |  | Alicia, Jana, Nazgul, Sviatlana, Poppy
2 | 2023-05-12 | High Level Design: finalizing text, diagram, having call, putting in template | 1 hour |  |  | Nazgul, Sviatlana, Alicia
2 | 2023-05-12 | Submittion of howework_2 to the mentor |  |  |  | Nazgul
2 | 2023-05-13 | Idea about better organization of work: Trello Workspace | 20 minutes |  |  | Jana
2 | 2023-05-13 | Reading API documentaion - Stock Market and News | 1 hour |  |  | Nazgul
2 | 2023-05-13 | Presentiaton of the idea about Flask as framework for the project |  |  |  | Poppy
2 | 2023-05-13 | Call: Group discussions about the main project feautures and objections. | 30 minutes |  |  | Sviatlana, Jana, Nazgul, Poppy
2 | 2023-05-13 | Summarising of the further steps and part of work |  |  |  | Nazgul
2 | 13/5/2023 | Creating virtual environment. Flask installation. Experimenting making basic webpages, rendering HTML templates, adding Bootstrap and Template inheritiance, GET and POST functions, login, remembering session data, logout, clearing data, message flashing. | 2 hours |  |  | Poppy
2 | 2023-05-13 | Preparing first prototype a piece of the code in Python (incl.API) (back end) - Stock Market | 1 hour |  |  | Nazgul
2 | 2023-05-14 | Call: Group discussions about the main project feautures and objections, preparing a sketch how pages should look like | 1 hour |  |  | Sviatlana, Alicia, Nazgul
2 | 14/5/2023 | Experimenting with SQLAlchemy. Connection with website. SQLite database, with user table created | 1.5 hours |  |  | Poppy
2 | 2023-05-14 | Preparing scheme via jamboard and doc file with the main features and detailes about every part of the project (back end, front-end, database, framework, vizualization part, email-notification): questions for discussion | 1 hour |  |  | Nazgul, Alicia
3 | 2023-05-15 | Additions to scheme and doc file |  |  |  | Sviatlana
| 15/05/2023 | News Part: preparing sample code to grab data from News API | 1 hour |  |  | Nazgul
3 | 15/05/2023 | Call: discussing and considering web-server, registration coding part | 1 hour |  |  | Alicia, Nazgul, Sviatlana, Poppy
3 | 15/05/2023 | Made a basic website following tutorials - login, signup, data retention | 2.5 hours |  |  | Poppy
3 | 17/05/2023 | Notifications - Registration on SendGrid Service to send emails via this service, reading documentation | 1 hour |  |  | Nazgul
3 | 17/05/2023 | Notifications - Preparing sample code to send notifications with News in body via SendGrid, testing | 1 hour |  |  | Nazgul
3 | 17/05/2023 | Call: discussing prepared code samples: web-server, StockMarket data, News data, notifications, sharing responsibilities | 1 hour |  |  | Alicia, Jana, Nazgul, Sviatlana, Poppy
3 | 20/05/2023 | Call: discussing implementation of timer to run functions on set time and considering compatibility with other functions | 1 hour |  |  | Nazgul, Sviatlana
3 | 19/05/2023 | Looking into how to use Chart.js to insert graphs into our app and writing the code for it; packaging the functions that retrieve data through the API Alpha Vantage so that the data can be extracted in the right format for the graphs | 1:30 hours |  |  | Alicia
3 | 2023-05-19 | writing the views.py file for fetching stock values and news. Writing the home.html file for displaying | 5 hours |  |  | Jana
3 | 20/05/2023 | Call: Understanding the API call's output and how it feeds the graphs on our site to make the data visualization work | 3 hours |  |  | Alicia, Nazgul, Sviatlana, Jana
3 | 21/05/2023 | Call: registering a new project email at SendGrid and formatting code part for sending notifications | 1 hour |  |  | Nazgul, Sviatlana
4 | 22/05/2023 | Working on the user experience after log in and customising the look & feel. Ensuring the workflow from stock name definition to graph delivery on the front-end using chart.js works - delivery of 1 month, 1 year, 5 year data | 2:30 hours |  |  | Alicia
4 | 22/05/2023 | Call: talking about everyone's updates after the weekend and defining next steps with a focus on getting the connection with the SQL database up and running | 1:30 hours |  |  | Poppy, Nazgul, Svetlana, Jana, Alicia
4 | 22/05/2023 | Formatting codes to grab news based on set sources, sorted that the newest news come first, formatting code of notifications that user will receive 3 news at once | 2 hours |  |  | Nazgul
4 | 2023-05-22 | Updating the views.py file to fit the db/ Login/ SignUp. Also updating the home.html with graphs/ news data | 4 hours |  |  | Jana
4 | 24/05/2023 | Call: Discussion to see status of project; defining next steps and what is left to complete | 1 hour |  |  | Poppy, Nazgul, Svetlana, Alicia
4 | 25/05/2023 | Notifications: formatting codes of fetching_news to send to email in better format | 1 hour |  |  | Nazgul
4 | 25/05/2023 | Call: Debugging and fixing code, adding other checks for when the user registers, reviewing the entire workflow | 3 hours |  |  | Poppy, Alicia
4 | 25/05/2023 | Adding html files for opportunity to change password and stocks by users via web | 5 hours |  |  | Sviatlana
4 | 25/05/2023 | Debugging, fixing functions to grab the correct pricing elements from the dictionary generated through the API for stock data, researching and adding README template | 1 hour |  |  | Alicia
4 | 26/05/2023 | Retention of correct sign-in information implemented if there other errors on page. Error message returned if invalid ticker symbol inserted on sign in page. | 1 hour |  |  | Poppy
4 | 26/05/2023 | Formatting fetch_stock_data() that it reflects up and down sign in correct way, adding functions to get news for messaging and sending notifications | 2 hour |  |  | Nazgul
4 | 27/05/2023 | Call: discussing, fixing codes that notifications can work and so on | 1 hour |  |  | Alicia, Jana, Nazgul, Sviatlana, Poppy
4 | 27/05/2023 | Adding code for opportunity to change send notifications via e-mail of the user when the limit for price changing reached (together with news notification) | 5 hours |  |  | Nazgul, Sviatlana
4 | 27/05/2023 | Implemented retention of content when an errror with log in / sign up. Ensured only legitimate stock symbols could be entered at sign up and when changing stock settings. | 2 hours |  |  | Poppy
4 | 28/05/2023 | Tests for functions in views.py file | 2 hours |  |  | Sviatlana
4 | 2023-05-28 | Writing test files | 2.5 hours |  |  | Jana
4 | 28/05/2023 | Updated README content. Created tests for auth.py | 4 hours |  |  | Poppy
4 | 28/05/2023 | Pulling together the resources ready for submission. | 4 hours |  |  | Alicia, Jana, Nazgul, Sviatlana, Poppy
Total time: